## Sheet1
ChangeRequests / AllProject (30-2017 - 30-2017)
Description | Applicant | Project | Impact | Node | Hostname | Start date | End date | Note | Status | Testmanager | Conflicting project | 30-2017
VM Switched to Unisys VM PIM SIT 1 | Martin Groeneveld | Future of Mobile Step 5 | No impact | PIM | PIM SIT1 | 21-07-2017 10:00 | 24-07-2017 17:00 |  | Accepted
New CBS hardware and upgrade to 17.7 | Eugene Tonino | New CBS Hardware | Impact | BOSS | NGBSS SIT2 | 21-07-2017 9:00 | 26-07-2017 20:00 | Further | Accepted | Verhaeg Leon | VoLTE BM Mobile Only | Test uitvoering
Update iPIT 3.0 | Martin Groeneveld | Test tooling en automatisering | No impact | iPIT 3.0 | IPIT_HOST | 27-07-2017 11:00 | 27-07-2017 13:00 |  | Accepted
Update Mavenir VMS from R1E1.3 to R1E1.5 | Willem Alkemade | Converged Messaging | No impact | Voicemail Platform | Mavenir VMS (Rt site) | 27-07-2017 9:00 | 27-07-2017 19:00 | R1E1.3 to RE1.4 | In progress
BOG Upgrade 14.2 | Fred Boon | BOG upgrade to 14.2 | No impact | BOG | BOG | 27-07-2017 9:00 | 27-07-2017 17:00 | BOG | In progress