## Sheet1
ChangeRequests / AllProject (31-2017 - 32-2017)
Description | Applicant | Project | Impact | Node | Hostname | Start date | End date | Note | Status | Testmanager | Conflicting project | 31-2017 | 32-2017
Update Mavenir VMS from R1E1.3 to R1E1.4 | Willem Alkemade | Converged Messaging | No impact | Voicemail Platform | Mavenir VMS (Asd site) | 31-07-2017 9:00 | 31-07-2017 17:00 |  | In progress
Update Mavenir VMS from R1E1.3 to R1E1.4 | Willem Alkemade | Converged Messaging | No impact | Voicemail Platform | Mavenir VMS (Rt site) | 31-07-2017 9:00 | 31-07-2017 17:00 |  | In progress
Update Mavenir VMS from R1E1.3 to R1E1.5 | Willem Alkemade | Converged Messaging | No impact | Voicemail Platform | Mavenir VMS (Rt site) | 31-07-2017 9:00 | 31-07-2017 19:00 | R1E1.4 to RE1.5 | In progress
BOG Upgrade 14.2 | Fred Boon | BOG upgrade to 14.2 | No impact | BOG | BOG | 03-08-2017 9:00 | 03-08-2017 17:00 | Extra session needed (BOG-RT) | In progress | Muste Madalina | BOG upgrade to 14.2 | Test uitvoering